## Story Assignments
Story ID	Story	Story Points	Priority	Hrs Remaining	Assigned To	Comments, Blockages
M00	As a user I would like to be able to add a widget to the dashboard	2	1 - Hi		(1) Open	Example story with 4 ACs
M00.1	Widget class that all widgets inherit from	1	2 - Med		(1) Open	Jasmin
M00.2	Widget can be added by clicking a "plus" icon	1	2 - Med		(1) Open	Charlie

M00.3	A "minus" icon appears when there are over 0 widgets	1	2 - Med		(1) Open	Charlie
	Clicking the minus icon allows user to select a widget to remove.	1	2 - Med		(1) Open	Charlie

M00.5	Widget clears when clicked in removeMode	1	2 - Med		(4) Blocked
	removeMode is exited immediately after widget clears.	1	2 - Med		(4) Blocked

M01	As a user I would like to be able to resize widgets	3	1 - Hi		(4) Blocked
	Widget can be resized	1	2 - Med
	Widgets cannot overlap	2	1 - Hi

M04	Best performing and worst performing goals widgets	5	3 - Lo		(4) Blocked	Jeremy
	Best catagories widget (Displays the top three performing goals)	2	3 - Lo
	Worst catagories widget (worst 3 performing areas)	2	3 - Lo
	Ability to add a custom widget	1	3 - Lo

M04	As a user I would like to view data in a widget	8	2 - Med		(1) Open	IHasData implementation ?
	Widget displays single measurement appropriately	3				Erik
	Widget displays to current month of data entry by default	2
	Widget signifies to user that no data exists for month when applicable.	1
	Widget can switch back and forward a month	1
	Widget can change measurement types	2

E00	As a user I would like to add, and view, measurements and goal info	8	1 - Hi		(1) Open	Not in widgets, in original tool Shane
E01	User must be able to add as many measurements as they wish.	2	1 - Hi		(1) Open	No crashes, no failed saves. in original tool
E02	User can call up previous measurements and info	1	1 - Hi		(1) Open
E03	User can enter monthly data	2	1 - Hi			Required to unblock testing.
E04	Must be able to do all of the above with an empty database.	3	1 - Hi		(4) Blocked	This task might be a 5....

M05	Dashboard saves widgets between loads	5	2 - Med		(4) Blocked	Matt
	Dashboard looks the same when program is closed and reloaded.	2
	Possitions and sizes of widgets are saved	2
	Widgets do not overlap	1

M03	Unit test coverage analysis / number of controllers that need tests (SPIKE)	1	1 - Hi		(1) Open	Matt 43 failing

	Comments
	31 Story points
	5 blocked story points

## Burndown
	Eric	Jeremy	Shane	Charlie	Matt	Jasmin
9/10/2015	8	18	4	4	0	6
9/11/2015	8	16	3	4	0	5
9/12/2015	7	14	2	4	0	1
9/13/2015	6	12	1	4	0	1
9/14/2015
9/15/2015
9/16/2015
9/17/2015
9/18/2015
9/19/2015
9/20/2015
9/21/2015
9/22/2015
9/23/2015